## Sheet1
Activity	Description	Duration	Predecessor
1	Architectural Decisions	10	0
2	Internal Specifications	20	1
3	External Specifications	18	1
4	Feature Specifications	15	1
5	Voice Recognition	5	2,3
6	Case	4	2,3
7	Screen	2	2,3
8	Speaker Output Jacks	2	2,3
9	Tape Mechanism	2	2,3
10	Databse	40	4
11	Microphone/Soundcard	5	4
12	Pager	4	4
13	Barcode Reader	3	4
14	Alarm Clock	4	4
15	Computer I/O	5	5,6,7,8,9,10,11,12,13,14,15
16	Review Design	10	5,6,7,8,9,10,11,12,13,14,15,
17	Price Components	5	16,17
18	Integration	15	16
19	Document Design	35	18
20	Procure Prototype Components	20	20
21	Assemble Prototypes	10	21
22	Lab test Prototypes	20	19,22
23	Field Test Prototypes	20	23
24	Adjust Design	20	24
25	Order Stock Parts	2	24
26	Order Custom Parts	2	25
27	Assemble First Production Uni	10	26
28	Test Unit	10	27
29	Produce 30 Units	15	28
30	Train Sales Representatives	10	29