## Sheet1
Activity	Description	Event	Response	Contingency
1	Architectural Decisions	Planning is Delayed	Enforce strict timetable	Status review often
2	Internal Specifications	Planning is Delayed	Enforce strict timetable	Status review often
3	External Specifications	Planning is Delayed	Enforce strict timetable	Status review often
4	Feature Specifications	Planning is Delayed	Enforce strict timetable	Status review often
5	Voice Recognition	Parts Delayed	Order from trusted supplier	Order from backup supplier
6	Case	Case Delayed	Ensure case designers are kept informed to avoid	Have backup supplier
7	Screen	Screen Delayed	Order from trusted supplier	Have backup supplier
8	Speaker Output Jacks	Speaker Delayed	Order from trusted supplier	Have backup supplier
9	Tape Mechanism	Tape Delayed	Ensure parts are ordered friom trusted supliers	Have backup supplier
10	Databse	Database Delayed	Ensured workload is possible for team size	Reallocate resources to help team finish on time
11	Microphone/Soundcard	Microphone Delayed	Ensure parts are ordered friom trusted supliers	Have backup supplier
12	Pager	Pager Delayed	Ensure parts are ordered friom trusted supliers	Have backup supplier
13	Barcode Reader	Reader Delayed	Ensure parts are ordered friom trusted supliers	Have backup supplier
14	Alarm Clock	Clock Delayed	Ensure parts are ordered friom trusted supliers	Have backup supplier
15	Computer I/O	I/O delayed	Ensure parts are ordered friom trusted supliers	Have backup supplier
16	Review Design	Work slowed due to low morale and overwork	Ensure team morale is not allowed to severely decrease	Company team building activity
17	Price Components	Work slowed due to difficulty in obtaqining data to gauge price	Reallocate resources to help team find resources sooner	Price product using different strategy
18	Integration	Integrating parts takes longer than expected	Set up team meetings	Set up team discussion so everyone thoroughly understands the project
19	Document Design	Slow design	Speed up design timetable	Reallocate team times
20	Procure Prototype Components	Slow delivery	Use trusted vendors	Use multiple vendors
21	Assemble Prototypes	Assembly problems	Reasses prototype assembly	Find anther approach to assembly
22	Lab test Prototypes	Testing discoveres bugs	Fix Bugs	Reallocate resources to fix bugs faster
23	Field Test Prototypes	Field test discoveres bugs	Fix Bugs	Reallocate resources to fix bugs faster
24	Adjust Design	Redesign Delayed	Fix Bugs	Reallocate resources to fix bugs faster
25	Order Stock Parts	Stock parts delayed	Use multiple vendors	Use trusted vendors
26	Order Custom Parts	Custom parts delayed	Use multiple vendors	Use trusted vendors
27	Assemble First Production Uni	Assembly encounters problems	Rewrite manual witht corrected instructions	Team meeting to come up with different assembly strategy
28	Test Unit	Problems are uncovered	Reinstate to the team the importance of delivering a quality product	Make sure testing is thorough
29	Produce 30 Units	Units are delayed or under quality	Be specific about the product	Use multiple suppliers
30	Train Sales Representatives	Sales team is not filled by deadline	Use remaining money to increase incentives for hireing	Use remaining money to hire experienced sales personel